## A) Apex PH Activation Flow
# | Screen | Notes | Estimates (hrs)
0.0 | Agents Introduction | 1. Design an introductory screen that presents all five BuildParty agents (Nova, Echo, Orbit, Flare, Apex) before the user enters the Apex flow -- gives the full agent ecosystem context upfront 2. Each agent gets a custom 3D mascot/avatar to give them distinct personality and make the lineup visually memorable -- concepts will be created in an existing Stitch project | 3
1.0 | Apex is running | 1. While a scan step is active, make it visually prominent -- highlight the card currently being processed (not just a thin gray line) 2. Add a pixelation/dissolve effect on the item being scanned -- pixelated while working, resolves into final result when done 3. Show real-time tool-call annotations during the scan (e.g. Running decode skill, Scanning Product Hunt top 10) 4. Show a preview of the output from the agent for each completed step on the right side | 2
1.0.1 | Apex run complete
1.1 | Apex Admin Dashboard | 1. Rename the CMT column label to Comments 2. Add a BuildParty lifecycle status column showing where each founder is in the flow (e.g. Draft Sent, Signed Up, Session Confirmed, etc.) | 0.5
1.1.1 | Outreach Draft Modal
1.1.2 | Outreach Sent Success Overlay
1.2 | Community Profile Page
1.2.1 | Decode Page | 1. Page must be BuildParty-branded throughout -- make it unambiguous this is a BuildParty Decode, not Velo's own page 2. Add a BuildParty navigation header/menu so users can get back to the rest of the app from the Decode page | 2
1.2.2 | Microcourse Page | 1. Page must be BuildParty-branded throughout -- same brand treatment as the Decode page 2. Add a BuildParty navigation header/menu so users can navigate back to the app 3. Make it unambiguous that this is BuildParty's microcourse on Velo | 1.5
2.0 | Founder checks Gmail inbox
2.1 | Founder opens BuildParty email | 1. Redesign as a full, polished HTML email -- this is the first impression and needs to look impressive 2. Rob flagged this as a blocker -- must be done before moving on | 2
3.0 | BuildParty Sign-Up Screen
3.1 | BuildParty Profile Details
3.2 | What to Expect Screen | 1. Lead with the exciting content (Decode + Microcourse) -- currently the interesting stuff is below the fold and the founder won't scroll 2. Reduce white space above the fold; consider a brief table of contents or visual preview at the top | 1
3.3 | Slot Selection Screen
3.4 | Session Confirmation Screen
4.0 | Luma Event Page Live
5.0 | Discovery Page
5.0.1 | Session Preview Panel + RSVP
5.0.2 | You're in! Overlay
5.0.3 | Rob clicks 'Join the PreParty'
6.0 | Nova: PreParty Lobby | 1. Add a pulsating ring animation around the presenter/agent avatar (like the Delphi / Keith Rabois demo) 2. Add session state indicators: Live (green), Up Next (yellow/neutral), Starting Soon (countdown) 3. Show a session timeline (elapsed time + time remaining, like a YouTube progress bar) 4. Make it definitively clear where users are in the session -- current layout is ambiguous | 3